## Key_Notes
Program (model)
Platform
Production Year
Tracker Latest review (date):
By: | Ꙭ
|  | NPI | Lineup
SOP: | 2025-08-15 | ▪ | □
Gate timeline: | G1 | G2 | G3 | G4 | G5 | G6
Reocurring Gate ceremonies | G1 | G2 | G3 | G4 | G5 | G6
Kickoff (1:1) | ▪ | □ | □ | □ | □ | □
Interim review for conditional approval (work team) | ▪ | □ | □ | □ | □ | □
Gate review (1:1) | ▪ | □ | □ | □ | □ | □
Retro (PgMeeting) | □ | □ | □ | □ | □ | □
Pg Recommendation and Action plan (EMT) | □ | □ | □ | □ | □ | □
REQUIRED TRACKING DOCUMENTATION (Change mgmt)
xBOM (PN based changes)
Technical specifications sheet (characteristic changes)
Option package sheet (SKU driver)
To "officially" add a Gate deliverable | Create a new line for it
Reference:
https://taigamotors.sharepoint.com/sites/Taiga.Product.Development/Shared%20Documents/SNOWMOBILE/TS04.3/Snow%20PDP%20Tracker%20-%20TS04.3.xlsx?web=1
2024-05-25
Max's recommendations:
- Begin the TPDP process for TS04.4 by early June.
- Before starting, review deliverables, discuss challenges, 1:1 with all managers.
- Have ENG project managers discuss/define the details of each deliverable with their teams.
- Expect the process to be in a "maleable" state until the completion of TS05.1, hence once minimum 1 NPI is made.
(Deliverables can be added, removed and modified as long as the impacts have been reviewed, risks assessed.)
- Track the advancement of the 3 Program documents at the PSP. (dashboard)
- Reassess the gate status with the stakeholders 1:1 a couple weeks before the Gate deadline.
- Present the Gate status at the Program Meeting once the recommendations have been addressed at the EMT.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: example

## New_Platform
GATE | G0 |  |  | G1 |  |  | G2 |  |  | G3 |  |  | G4 |  |  | G5 |  |  | G6+
Typical duration (SOP - Months) | -33 |  |  | -27 |  |  | -23 |  |  | -17 |  |  | -13 |  |  | -5 |  |  | 2
Expected start | 2022-11-12 12:00 |  |  | 2023-05-14 12:00 |  |  | 2023-09-13 12:00 |  |  | 2024-03-14 12:00 |  |  | 2024-07-14 12:00 |  |  | 2025-03-15 12:00 |  |  | 2025-10-15
Gate Status | Closed |  |  | Closed |  |  | Closed |  |  | Closed |  |  | Closed |  |  | Closed |  |  | Closed
| Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date)
Program | GATE KICK-OFF |  |  | GATE KICK-OFF |  |  | PLAN TIMELINE CONFIRMATION |  |  | DWG AND TOOLING RELEASE PLAN |  |  | TEAM COMPOSITION |  |  | FINAL SAFETY REVIEW |  |  | PROGRAM DOCUMENTS UPDATED AND RELEASED
| RESOURCE RISK ASSESSMENT |  |  | RESOURCE RISK ASSESSMENT |  |  | RESOURCE RISK ASSESSMENT |  |  | PROJECT RISK ASSESSMENT |  |  | PROJECT RISK ASSESSMENT |  |  | PROJECT RISK ASSESSMENT |  |  | PROJECT RISK ASSESSMENT
| GATE PLAN OVERVIEW (Time & Budget) |  |  | SET GATE SCHEDULE |  |  | SCHEDULE STATUS |  |  | SCHEDULE STATUS |  |  | SCHEDULE STATUS |  |  | SCHEDULE STATUS |  |  | SCHEDULE STATUS
| COMPETITION BOARD |  |  | PROJECT CHARTER (DEFINITION) |  |  | CAPEX ESTIMATE |  |  | TOOLING CAPEX APPROVAL (Based on VP Assessment) |  |  | COST FOLLOW UP W/ REAL QUOTES |  |  | COST FOLLOW UP |  |  | COST FOLLOW UP
| TARGET BUSINESS CASE (OPEX, CAPEX, margin) |  |  | PRELIM BUSINESS CASE (OPEX, CAPEX, margin) |  |  | REVIEW BUSINESS CASE |  |  | REVIEW BUSINESS CASE | [8 empty] | POST MORTEM
| TEAM COMPOSITION |  |  | TEAM COMPOSITION (Set Stakeholder roles) |  |  | TEAM COMPOSITION |  |  | TEAM COMPOSITION
| Other actions: Gate Presentation Gate Program recommendations (for EMT) Lessons Learned Provide previous MY BOM Cost to Finance |  |  | Other actions: Gate Presentation Gate Program recommendations (for EMT) Lessons Learned Evaluate Proof of Concept Identify project portfolio constraints |  |  | Other actions: Initial Design Review Make vs Buy Assessment Product Intro/Obsolescence plan Pricing draft Gate Presentation Gate Program recommendations (for EMT) Lessons Learned Initial Safety Assessment |  |  | Other actions: BOM Cost Release and Approval Gate Presentation Gate Program recommendations (for EMT) Lessons Learned Initial Safety Assessment Estimate spare volumes Evaluate obsolescence mgmt and inventory |  |  | Other actions: Gate Presentation Gate Program recommendations (for EMT) |  |  | Other actions: Gate Presentation Gate Program recommendations (for EMT) Production approval Definition of critical KPI to track during production |  |  | Other actions: Gate Presentation Identify contunuous improvements and corrective actions Compare actual performance to targets
Engineering | LIFESTYLE BOARD |  |  | DESIGN VISION BOARD |  |  | FULL 3D MODEL (xBOM Creation) |  |  | PRELIM. BOM RELEASE (R15) |  |  | TT DVP&R COMPLETION |  |  | LIST OF APPROVED NCDS
|  |  |  | PRODUCT DEFINITION BOARD |  |  | CONCEPT DEFINITION |  |  | VP DESIGN AND 2D RELEASE (R15) |  |  | TT (R30) DWG RELEASE |  |  | PRODUCTION (R60) DWG RELEASE
|  |  |  | INDUSTRIAL DESIGN IDEATION (RENDER) |  |  | PRELIM. ERGO / HUMAN FACTOR BOARD |  |  | FINAL CONCEPT DEFINITION |  |  | VP DVP STATUS |  |  | FIT&FINISH REVIEW
|  |  |  | MODEL WALK AROUND (CLAY OR VR) |  |  | P0 VEHICLE BUILD |  |  | PRODUCT PERFORMANCE RECORD (REQUIREMENTS ARE MET) |  |  | VEHICLE RELIABILITY STATUS |  |  | VEHICLE RELIABILITY STATUS
[7 empty] | FIT AND FORM TARGETS |  |  | FIT AND FORM REVIEW | [5 empty] | PFPS STATUS
[7 empty] | DVP&R CREATION |  |  | VP DVP&R COMPLETION
[7 empty] | SURFACES RELEASE PLAN |  |  | SURFACE AND LABEL DIE LINE RELEASE STATUS
[7 empty] | RELIABILITY PLAN AND SAFETY REVIEW |  |  | GLASS CASE (INDUSTRIAL DESIGN REVIEW)
| Other actions: Feasibility Concept (P0) |  |  | Other actions: Team k-o Initial sketch Design for function / Narrow down concepts Prelim. Product requirements |  |  | Other actions: Initial technical specifications Confirmed ENG Requirements Order Samples Dynamic Feasibility Risk and Requirement Prioritization |  |  | Other actions: DFMEA VP Testing TT DVP Creation Bench Testing Plan K-O |  |  | Other actions: Design transfer to production DMU Creation Validate MKTG Hero Stats and requirements |  |  | Other actions: Release vehicle FW Release app Release BOMs |  |  | Other actions: Compare actual product specifications to the initially approved specs
Quality |  |  |  | QA PLAN K-O |  |  | QE PLAN |  |  | QE PLAN STATUS |  |  | QE PLAN STATUS |  |  | QE PLAN STATUS |  |  | QE PLAN STATUS
|  |  |  | SQA TARGETS |  |  | SQA PLAN |  |  | DESIGN FOR QUALITY EVALUATED ON VP |  |  | RELEASE SQAM AND PPAP TIMELINE |  |  | PPAP ACCESSORIZING PLAN STATUS |  |  | PPAP STATUS
| Other actions: |  |  | Other actions: Fixture CAPEX estimate Lessons Learned review |  |  | Other actions: QC Fixtures and Budget PPAP Requirement identification |  |  | Other actions: Review SQAM New Design Concept Approval |  |  | Other actions: Inspect DWGs Initiate equipment and process qualification |  |  | Other actions: Review IQ/OQ/PQ Final supplier production control plan review |  |  | Other actions: Audit production launch
Compli-ance |  |  |  | COMPLIANCE PLAN |  |  | IDENTIFICATION OF STANDARDS TO MEET |  |  | MEDIUM RISK REQUIREMENT EVALUATION |  |  | FINAL DESIGN MEETS COMPLIANCE REQUIREMENTS |  |  | CERTIFICATION RECEPTION PLAN STATUS |  |  | CERTIFICATION RECEPTION STATUS
HIGH RISK REQUIREMENT EVALUATION
IP / Legal |  |  |  | INITIAL PATENT SEARCH |  |  | PRELIM IP MARKET CLEARANCE |  |  | APPLY FOR PATENT PROTECTION |  |  | APPROVE MKTG CLAIMS |  |  | FINAL IP MARKET CLEARANCE
PATENT FREEDOM TO OPERATE RISK ASSESSMENT
Manufac-turing |  |  |  | MFG DEFINITION BOARD |  |  | PRODUCTION PLAN K-O |  |  | DFA AND PFD EVALUATED ON VP |  |  | OPERATIONS PLAN STATUS |  |  | OPERATION PLAN STATUS |  |  | LAUNCH PRODUCTION
|  |  |  | OPERATIONAL TARGETS | [5 empty] | OPERATIONS PLAN STATUS | [8 empty] | FINAL PRODUCTION READINESS VERIFICATION
| Other actions: |  |  | Other actions: |  |  | Other actions: Identify long lead equipment CAPEX estimate Identify design impacts to production |  |  | Other actions: MFG Equipment Plan PFMEA |  |  | Other actions: TT Builds on the assembly line mBOM Release DFM/A Final Review Purchase production equipment |  |  | Other actions: Schedule production Ramp-up plan |  |  | Other actions:
Procurement |  |  |  | SOURCING TARGETS |  |  | SOURCING PLAN |  |  | PROCUREMENT PLAN STATUS |  |  | FINALIZE CONTRACTS AND DFM REVIEW
|  |  |  | GLOBAL SOURCING DEFINITION BOARD |  |  | SUBMIT RFQ AND NDA |  |  | SQA PLAN STATUS |  |  | TT RECEPTION PLAN
| Other actions: |  |  | Other actions: New supplier assessment Market pricing benchmark |  |  | Other actions: Identify supplier candidates Estimate leadtimes and costs (per commodity) Complete supplier assessment Provide complete "Expected BOM Cost" |  |  | Other actions: Communicate T&C Develop and Approve Suppliers Provide Quote Based BOM Cost |  |  | Other actions: Place tooling POs Update ERP |  |  | Other actions: Obtain PPAP approval Obtain CM's part warranty Release the final real BOM Cost to program |  |  | Other actions:
Sales/Comm ops | PRELIM. CUSTOMER REQUIREMENTS |  |  | FINAL CUSTOMER REQUIREMENTS |  |  | FREEZE SALES REQUIREMENTS |  |  | DESIGN FOR SERVICEABILITY |  |  | SERVICE PART PLAN |  |  | RELEASE OPERATOR'S MANUAL |  |  | CUSTOMER EXPERIENCE READINESS
|  |  |  | IDENTIFY COMPETITION |  |  | GATHER CUSTOMER AND SERVICING FEEDBACK |  |  | FORECAST VOLUME AND PRICE |  |  | OPTION PACKAGE SHEET REVIEW |  |  | SALES SPECIFICATION REVIEW |  |  | NETWORK READINESS
|  |  |  | USER EXPERIENCE TARGETS AND DEFINITION BOARD |  |  | K-O CUSTOMER EXPERIENCE PLAN |  |  | CUSTOMER EXPERIENCE PLAN STATUS |  |  | CUSTOMER EXPERIENCE PLAN STATUS |  |  | CUSTOMER EXPERIENCE PLAN STATUS
|  |  |  | NETWORK TARGETS |  |  | NETWORK PLAN |  |  | NETWORK PLAN STATUS |  |  | NETWORK PLAN STATUS
| Other actions: Setup claims matrix Define product Ethos |  |  | Other actions: Sales strategy Target warranty |  |  | Other actions: |  |  | Other actions: Technical Publication Preparation Determine servicing part volumes Confirm customer requirements are met |  |  | Other actions: Verify market demand Complete market-facing NPI Manual review K-O |  |  | Other actions: Release production service documents Complete service part list Place service part POs
Marketing | PRODUCT DEFINITION |  |  | MARKET EVALUATION PLAN |  |  | PRODUCT LAUNCH PLAN K-O |  |  | MARKETING VEHICLE PLAN |  |  | FINAL NAMING |  |  | ACCESSORIZING PLAN STATUS |  |  | MONITOR EARLY FEEDBACK
|  |  |  | PRELIM. PRODUCT CONFIGURATIONS / PACKAGES |  |  | PRODUCT CONFIGURATION CONFIRMATION |  |  | EVALUATION RERPORT ON VP |  |  | ACCESSORY GLASS CASE (3D MODELS) | [5 empty] | ACCESSORY READINESS
|  |  |  | ACCESSORIZING PLAN |  |  | ACCESSORIZING PLAN STATUS AND CONCEPT APPROVAL |  |  | DESIGN FOR ACCESSORIZING |  |  | ACCESORY PLAN STATUS
[7 empty] | EVALUATION REPORT (of P0) |  |  | FINAL RENDER AVAILABLE FOR CONTENT CREATION |  |  | PRODUCT LAUNCH
NAMING PROPOSAL
LABEL DESIGN K-O
| Other actions: |  |  | Other actions: |  |  | Other actions: |  |  | Other actions: |  |  | Other actions: Release TT Decals Final Photography |  |  | Other actions: Review user documentation |  |  | Other actions:
Finnance |  |  |  | TARGET TOTAL BOM COST BUSINESS CASE |  |  | BOM COST TARGET REVIEW |  |  | SOP FINANCIAL JUSTIIFCATION (FORECAST VOLUME, CAPEX, OPEX) |  |  | DEFINE STANDARD COSTS | [5 empty] | COMPARE ACTUALS TO TARGETS
|  |  |  | FREEZE PREVIOUS MY BOM COST |  |  | COMPLETE BUDGET ANALYSIS

## LineUp_(Continuous_imp)
GATE | G0 |  |  | G4 |  |  | G5 |  |  | G6+
Typical duration (SOP - Months) | -18 |  |  | -12 |  |  | -5 |  |  | 2
Expected start | 2024-02-13 |  |  | 2024-08-14 |  |  | 2025-03-15 12:00 |  |  | 2025-10-15
Gate Status | Closed |  |  | Closed |  |  | Closed |  |  | Closed
| Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date) | Description | Status | Notes (Comp date)
Program | GATE KICK-OFF |  |  | LINEUP PROJECT APPROVAL |  |  | COST FOLLOW UP |  |  | PROGRAM DOCUMENTS UPDATED AND RELEASED
| RISK ASSESSMENT |  |  | PROJECT RISK ASSESSMENT |  |  | PROJECT RISK ASSESSMENT |  |  | POST MORTEM
| GATE PLAN OVERVIEW (Time & Budget) |  |  | SCHEDULE STATUS |  |  | SCHEDULE STATUS |  |  | SCHEDULE STATUS
| PRELIM. PROJECT LIST |  |  | COST FOLLOW UP W/ REAL QUOTES
| MARGIN TARGET |  |  | LINEUP MARGIN WITHIN BUDGET
| TEAM COMPOSITION |  |  | DWG AND TOOLING RELEASE PLAN
| Other actions: Gate Presentation Gate Program recommendations (for EMT) Lessons Learned Market comparison |  |  | Other actions: Gate Presentation Gate Program recommendations (for EMT) Obsolescence plan Generate serial numbers Tooling CAPEX Approval |  |  | Other actions: Gate Presentation Gate Program recommendations (for EMT) Production approval Definition of critical KPI to track during production |  |  | Other actions: Gate Presentation Identify contunuous improvements and corrective actions Compare actual performance to targets
Engineering | UPDATE LIFESTYLE BOARD |  |  | TT DVP&R AND (P)FPS STATUS |  |  | LIST OF APPROVED NCDS |  |  | LINEUP SUPPORT
|  |  |  | TT (R30) DWG RELEASE |  |  | PRODUCTION (R60) DWG RELEASE
|  |  |  | COLOR AND GRAPHIC RELEASE |  |  | VEHICLE RELIABILITY STATUS
VEHICLE RELIABILITY STATUS
TT EVALUATION REPORT
DESIGN VISION AND TREND BOARD
NEW CONCEPT DESCRIPTION LIST SUBMITTED
EBOM CREATION
| Other actions: Feasibility Concept |  |  | Other actions: DFMA review with Production DMU Creation Requirement and risk prioritization review Product performance record review DFMEA review |  |  | Other actions: Release vehicle FW Release app Release BOMs |  |  | Other actions: Compare actual product specifications to the initially approved specs
Quality | SQA TARGETS |  |  | QE PLAN STATUS |  |  | QE PLAN STATUS |  |  | QE PLAN STATUS
| QE TARGETS |  |  | PPAP DEVELOPMENT AND RECEIVING CLOSED |  |  | PPAP REVIEW |  |  | PPAP STATUS
| Other actions: Lessons learned review |  |  | Other actions: DWG Review Process and equipment review |  |  | Other actions: Review IQ/OQ/PQ Final supplier production control plan review |  |  | Other actions: Audit production launch
Compli-ance |  |  |  | FINAL DESIGN MEETS COMPLIANCE REQUIREMENTS |  |  | FINAL SAFETY REVIEW MINUTES |  |  | CERTIFICATION RECEPTION STATUS
INITIAL SAFETY REVIEW MINUTES
IP / Legal |  |  |  | FINAL IP MARKET CLEARANCE
Manufac-turing | OPS TARGETS |  |  | TT BUILD ON THE ASSEMBLY LINE |  |  | OPERATION PLAN STATUS |  |  | LAUNCH PRODUCTION
|  |  |  | OPERATIONS PLAN STATUS |  |  | PLANT READINESS STATUS |  |  | PLANT READINESS
| Other actions: |  |  | Other actions: mBOM Release DFM/A Final Review Purchase production equipment PFMEA review |  |  | Other actions: Schedule production Ramp-up plan |  |  | Other actions:
Procurement | PROCUREMENT TARGETS |  |  | MANUFACTURABILITY FEASIBILITY STATUS (DFM) |  |  | RELEASE FINAL PO
PROCUREMENT PLAN STATUS
SQA PLAN STATUS
| Other actions: New supplier assessment |  |  | Other actions: Place tooling POs Update ERP Final supplier selection Contract review |  |  | Other actions: Obtain PPAP approval Obtain CM's part warranty Release the final real BOM Cost to program |  |  | Other actions:
Sales/Comm ops | USER EXPERIENCE TARGETS |  |  | COMPETITION BOARD REVIEW |  |  | CUSTOMER EXPERIENCE PLAN STATUS |  |  | CUSTOMER EXPERIENCE READINESS
| NETWORK TARGETS |  |  | FINAL OPTION PACKAGE AND CONFIGURATIONS |  |  | REVIEW SALES SPECIFICATION |  |  | NETWORK READINESS
CUSTOMER EXPERIENCE PLAN STATUS
NETWORK PLAN STATUS
| Other actions: Update claims matrix Update product Ethos |  |  | Other actions: Customer requirements review Forecast volume and price User manual review Option package sheet review |  |  | Other actions: Release production service documents Complete service part list Place service part Pos
Marketing | PRELIM. OPTION PACKAGE/CONFIGURATIONS |  |  | NAMING REVIEW |  |  | ACCESSORIZING PLAN STATUS |  |  | ACCESSORY READINESS
| ACCESSORY INTEGRATION TARGETS |  |  | NEW ACCESSORY GLASS CASE (3D MODELS)
ACCESORY PLAN STATUS
LABEL REVIEW
| Other actions: Voice of the customer |  |  | Other actions: Release TT Decals Final Photography |  |  | Other actions: Review user documentation |  |  | Other actions:
Finnance | FREEZE PREVIOUS PROGRAM BOM PART COSTs |  |  | REVIEW STANDARD COSTS | [5 empty] | COMPARE ACTUALS TO TARGETS

## ENUMS
GATE Status | Status | Platform
Closed | To Do | Watercraft
Go | Ready for review | Snowmobile
Conditional Go | Approved
Hold | Conditional Approval
Recycle | Rejected
Kill